## Sites
Location Key | Permit | Build Status | Fibre Ready | Integration Test | Acceptance | Blocker Notes
DE-NRW-0107 | APPROVED | DONE | 18.09.2026 | PENDING | NOT_STARTED | Backhaul handover moved by supplier
DE-BY-0002 | APPROVED | DONE | 07.08.2026 | PENDING | NOT_STARTED
DE-BE-0003 | APPROVED | DONE | 08.08.2026 | PENDING | NOT_STARTED | Added late by partner spreadsheet
DE-HH-0004 | APPROVED | DONE | 09.08.2026 | PENDING | NOT_STARTED
DE-SN-0005 | APPROVED | DONE | 10.08.2026 | PENDING | NOT_STARTED
DE-BW-0006 | APPROVED | DONE | 11.08.2026 | PENDING | COMPLETE
DE-NI-0007 | PENDING | DONE | 12.08.2026 | PENDING | NOT_STARTED
DE-HE-0008 | APPROVED | DONE | 13.08.2026 | PENDING | NOT_STARTED
DE-NRW-0009 | APPROVED | DONE | 14.08.2026 | PENDING | NOT_STARTED
DE-BY-0010 | APPROVED | DONE | 15.08.2026 | PENDING | NOT_STARTED
DE-BE-0011 | APPROVED | DONE | 16.08.2026 | PENDING | NOT_STARTED
DE-HH-0077 | APPROVED | DONE | 18.08.2026 | PENDING | NOT_STARTED
DE-BW-0014 | APPROVED | DONE | 19.08.2026 | PENDING | NOT_STARTED
DE-NI-0015 | APPROVED | DONE | 10.08.2026 | PENDING | NOT_STARTED
DE-HE-0016 | APPROVED | DONE | 21.08.2026 | PENDING | NOT_STARTED
DE-NRW-0017 | APPROVED | DONE | 22.08.2026 | PENDING | NOT_STARTED
DE-BY-0018 | APPROVED | DONE | 23.08.2026 | PENDING | NOT_STARTED
DE-BE-0019 | APPROVED | DONE | 24.08.2026 | PENDING | NOT_STARTED
DE-HH-0020 | APPROVED | DONE | 25.08.2026 | PENDING | NOT_STARTED
DE-SN-0021 | APPROVED | DONE | 26.08.2026 | PENDING | NOT_STARTED
DE-BW-0022 | APPROVED | DONE | 27.08.2026 | PENDING | NOT_STARTED
DE-NI-0023 | APPROVED | DONE | 28.08.2026 | PENDING | NOT_STARTED
DE-HE-0024 | APPROVED | DONE | 29.08.2026 | PENDING | NOT_STARTED
DE-NRW-0025 | APPROVED | DONE | 30.08.2026 | PENDING | NOT_STARTED
DE-BY-0026 | APPROVED | DONE | 31.08.2026 | PENDING | NOT_STARTED
DE-BE-0027 | APPROVED | DONE | 01.09.2026 | PENDING | NOT_STARTED
DE-HH-0028 | APPROVED | DONE | 02.09.2026 | PENDING | NOT_STARTED
DE-SN-0029 | APPROVED | DONE | 03.09.2026 | PENDING | NOT_STARTED
DE-BW-0030 | APPROVED | DONE | 04.09.2026 | PENDING | NOT_STARTED
DE-NI-0031 | APPROVED | DONE | 05.09.2026 | PENDING | NOT_STARTED
DE-HE-0032 | APPROVED | DONE | 06.09.2026 | PENDING | NOT_STARTED
DE-NRW-0033 | APPROVED | DONE | 07.09.2026 | PENDING | NOT_STARTED
DE-BY-0034 | APPROVED | DONE | 08.09.2026 | PENDING | NOT_STARTED
DE-BE-0035 | APPROVED | DONE | 09.09.2026 | PENDING | NOT_STARTED
DE-HH-0036 | APPROVED | DONE | 10.09.2026 | PENDING | NOT_STARTED
DE-SN-0037 | APPROVED | DONE | 11.09.2026 | PENDING | NOT_STARTED
DE-BW-0038 | APPROVED | DONE | 12.09.2026 | PENDING | NOT_STARTED
DE-NI-0039 | APPROVED | DONE | 13.09.2026 | PENDING | NOT_STARTED
DE-HE-0040 | APPROVED | DONE | 05.08.2026 | PENDING | NOT_STARTED
DE-NRW-0041 | APPROVED | DONE | 06.08.2026 | PENDING | NOT_STARTED
DE-BY-0042 | APPROVED | DONE | 07.08.2026 | PENDING | NOT_STARTED
DE-BE-0043 | APPROVED | DONE | 08.08.2026 | PENDING | NOT_STARTED
DE-HH-0044 | APPROVED | DONE | 09.08.2026 | PENDING | NOT_STARTED
DE-SN-0045 | APPROVED | DONE | 10.08.2026 | PENDING | NOT_STARTED
DE-BW-0046 | APPROVED | DONE | 11.08.2026 | PENDING | NOT_STARTED
DE-NI-0047 | APPROVED | DONE | 12.08.2026 | PENDING | NOT_STARTED
DE-HE-0048 | APPROVED | DONE | 13.08.2026 | PENDING | NOT_STARTED
DE-NRW-0049 | APPROVED | DONE | 14.08.2026 | PENDING | NOT_STARTED
DE-BY-0050 | APPROVED | DONE | 15.08.2026 | PENDING | NOT_STARTED